## Detailed Schedule
Week 1 | May 15 - 21 | Task/Component Name | Estimated Effort (hrs) | Actual Effort (hrs) | Projected Client Hours | Actual Client Hours | Projected Mentor Hours | Actual Mentor Hours | Start Date | Completion Date
Module 1 - Course Introduction
|  | Start Brainstorming Ideas for Project | 2 | 3 | 0 | 0 | 0 | ? | 2017-05-15 | 2017-05-22
Week 2 | May 22 - 28 | Module 2 - Define Project
|  | Project Definition Background | 4 | 6 | 0.25 | 0.25 | 0 | ? | 2017-05-24 | 2017-05-28
Week 3 | May 29 - June 4 | Module 3 - Project Definition Section 1
|  | Project Definition Section 1 | 6 | 6 | 1 | 0.5 | 1 | ? | 2017-06-01 | 2017-06-04
Week 4 | June 5 - 11 | Module 4 - Project Definition Section 2, Project Status 1
|  | Project Definition Section 2 | 8 | 11 | 0 | 0 | 0.5 | ? | 2017-06-03 | 2017-06-11
|  | Project Status 1 | 2 | 2 | 1 | 0.25 | 0.5 | ? | 2017-06-10 | 2017-06-11
Week 5 | June 12 - 18 | Module 5 - Project Definition Section 3, Project Status 2
|  | Project Definition Section 3 | 5 | 4 | 0 | 1 | 0.5 | ? | 2017-06-12 | 2017-06-18
|  | Project Status 2 | 2 | 2 | 1 | 0.25 | 0.5 | ? | 2017-06-17 | 2017-06-18
|  | Create Risk Management Plan | 2 | 2 | 0 | 0 | 0.5 | ? | 2017-06-14 | 2017-06-18
|  | Create Risk Matrix | 1 | 1 | 0 | 0 | 0.5 | ? | 2017-06-14 | 2017-06-18
Week 6 | June 19 - 25 | Module 6 - Project Definition Section WBS, Project Status 3
|  | Project Definition Section WBS | 5 | 6 | 0 | 0 | 0.5 | ? | 2017-06-20 | 2017-06-25
|  | Project Status 3 | 2 | 2 | 1 | 0.25 | 0.5 | ? | 2017-06-24 | 2017-06-25
|  | Start Software Project Management Plan (SPMP) | 3 | 3 | 0 | 0 | 0 | ? | 2017-06-19 | 2017-06-25
|  | Create software budget and detailed timeline spreadsheet (SBDTS) | 3 | 5 | 1 | 1 | 0.5 | ? | 2017-06-19 | 2017-06-25
|  | Continue Working on Risk Management Plan | 3 | 2 | 0 | 0 | 0 | ? | 2017-06-22 | 2017-06-25
Week 7 | June 26 - July 2 | Module 7 - Progress Report 1
|  | Progress Report 1 | 3 | 5 | 2 | 0 | 0.5 | ? | 2017-06-30 | 2017-07-02
|  | Continue Working on Risk Management Plan | 3 | 1 | 0 | 0 | 0 | ? | 2017-06-30 | 2017-07-02
|  | Continue Working on SPMP | 8 | 0 | 0 | 0 | 0 | ? | 2017-07-02 | 2017-07-02
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-07-02 | 2017-07-02
Week 8 | July 3 - 9 | Module 8 - Project Status Update 4
|  | Project Status Update 4 | 2 | 2 | 1 | 0.5 | 0.5 | ? | 2017-07-09 | 2017-07-09
|  | Continue Working on Risk Management Plan | 2 | 2 | 0 | 0 | 0 | ? | 2017-07-03 | 2017-07-09
|  | Continue Working on SPMP | 3 | 5 | 2 | 0 | 0 | ? | 2017-07-05 | 2017-07-09
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-07-09 | 2017-07-09
Week 9 | July 10 - 16 | Module 9 - Project Status Update 5
|  | Project Status Update 5 | 2 | 1 | 1 | 0.5 | 0.5 | ? | 2017-07-16 | 2017-07-16
|  | Finish Risk Management Plan | 2 | 2 | 0 | 0 | 0 | ? | 2017-07-12 | 2017-07-16
|  | Continue Working on SPMP | 8 | 5 | 0 | 0 | 0 | ? | 2017-07-12 | 2017-07-16
|  | Update SBDTS | 1 | 1 | 0.5 | 0.5 | 0.5 | ? | 2017-07-16 | 2017-07-16
Week 10 | July 17 - 23 | Module 10 - Progress Report 2
|  | Progress Report 2 | 3 | 2 | 2 | 1 | 0.5 | ? | 2017-07-23 | 2017-07-23
|  | Start Working on PowerPoint Presentation | 3 | 1 | 0 | 0 | 0 | ? | 2017-07-23 | 2017-07-23
|  | Start Working on Software Requirements Specification (SRS) | 10 | 8 | 2 | 1 | 0.5 | ? | 2017-07-22 | 2017-07-23
|  | Finish SPMP | 5 | 9 | 2 | 1 | 0 | ? | 2017-07-17 | 2017-07-22
|  | Update SBDTS | 1 | 1 | 0.5 | 0.5 | 0.5 | ? | 2017-07-22 | 2017-07-23
Week 11 | July 24 - 30 | Module 11 - Project Status Update 6
|  | Project Status Update 6 | 2 | 1 | 1 | 1 | 0.5 | ? | 2017-07-30 | 2017-07-30
|  | Finish SRS | 10 | 17 | 1 | 2 | 0.5 | ? | 2017-07-24 | 2017-07-30
|  | Start Software Design Description (SDD) | 10 | 3 | 2 | 1 | 0 | ? | 2017-07-28 | 2017-07-30
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-07-30 | 2017-07-30
|  | Continue Working on PowerPoint Presentation | 2 | 2 | 0 | 0 | 0 | ? | 2017-07-24 | 2017-07-30
Week 12 | July 31 - August 2 | Module 12 - Final Report, YouTube and PowerPoint Presentations, Client Acceptance Letter, and all Project Artifacts
|  | Final Report | 5 | 3 | 1 | 1 | 2 | ? | 2017-07-31 | 2017-08-02
|  | YouTube Presentation | 3 | 3 | 1 | 1 | 2 | ? | 2017-07-31 | 2017-08-02
|  | Finish PowerPoint Presentation | 1 | 2 | 1 | 0.5 | 2 | ? | 2017-07-31 | 2017-08-02
|  | Client Acceptance Correspondence | 1 | 1 | 3 | 1 | 0.5 | ? | 2017-08-02 | 2017-08-02
|  | Finish Working on SDD | 10 | 12 | 2 | 1 | 2 | ? | 2017-08-02 | 2017-08-02
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-08-02 | 2017-08-02
Week 13 | August 3 - 6 | Module 13
|  | Start Designing User Interface | 8 | 5 | 2 | 1 | 0 | ? | 2017-08-06 | 2017-08-06
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-08-06 | 2017-08-06
Week 14 | August 7 - 13 | Module 14
|  | Continue Working on Designing User Interface | 8 | 3 | 2 | 0 | 0 | ? | 2017-08-07 | 2017-08-13
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-08-07 | 2017-08-13
Week 15 | August 14 - 20 | Module 15
|  | Finish Working on User Interface | 8 | 4 | 2 | 0 | 0 | ? | 2017-08-14 | 2017-08-20
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-08-14 | 2017-08-20
Week 16 | August 21 - 27 | Module 16
|  | Start Coding Project | 10 | 2 | 0 | 0 | 0 | ? | 2017-08-21 | 2017-08-27
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-08-21 | 2017-08-27
Week 17 | August 28 - September 3 | Module 17
|  | Continue Coding Project | 10 | 5 | 0 | 0 | 0 | ? | 2017-08-28 | 2017-09-03
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-08-28 | 2017-09-03
Week 18 | September 4 - 10 | Module 18
|  | Continue Coding Project | 10 | 4 | 0 | 0 | 0 | ? | 2017-09-04 | 2017-09-10
|  | Convert Project Definition Background to Report Format | 1 | 2 | 0 | 0 | 0.5 | ? | 2017-09-04 | 2017-09-10
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-09-04 | 2017-09-10
Week 19 | September 11 - 17 | Module 19
|  | Continue Coding Project | 10 | 6 | 0 | 0 | 0 | ? | 2017-09-11 | 2017-09-17
|  | Convert Project Definition Section 1 to Report Format | 2 | 2 | 0.5 | 0.5 | 0.5 | ? | 2017-09-11 | 2017-09-17
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-09-11 | 2017-09-17
Week 20 | September 18 - 24 | Module 20
|  | Continue Coding Project | 10 | 4 | 0 | 0 | 0 | ? | 2017-09-18 | 2017-09-24
|  | Project Status Update 1 | 2 | 2 | 0.5 | 0.5 | 0.5 | ? | 2017-09-18 | 2017-09-24
|  | Convert Project Definition Section 2 to Report Format | 1 | 1 | 0 | 0 | 0.5 | ? | 2017-09-18 | 2017-09-24
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-09-18 | 2017-09-24
Week 21 | September 25 - October 1 | Module 21
|  | Continue Coding Project | 10 | 8 | 0 | 0 | 0 | ? | 2017-09-25 | 2017-10-01
|  | Project Status Update 2 | 2 | 1 | 0.5 | 0 | 0.5 | ? | 2017-09-25 | 2017-10-01
|  | Convert Project Definition Section 3 and WBS to Report Format | 1 | 1 | 0 | 0 | 0.5 | ? | 2017-09-25 | 2017-10-01
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-09-25 | 2017-10-01
Week 22 | October 2 - 8 | Module 22
|  | Continue Coding Project | 10 | 5 | 0 | 0 | 0 | ? | 2017-10-02 | 2017-10-08
|  | Project Status Update 3 | 2 | 1 | 0.5 | 0 | 0.5 | ? | 2017-10-02 | 2017-10-08
|  | Update SBDTS | 1 | 0.5 | 0.5 | 0 | 0.5 | ? | 2017-10-02 | 2017-10-08
Week 23 | October 9 - 15 | Module 23
|  | Continue Coding Project | 10 | 3 | 0 | 0 | 0 | ? | 2017-10-09 | 2017-10-15
|  | Progress Report 1 | 3 | 2 | 0.5 | 0 | 0.5 | ? | 2017-10-09 | 2017-10-15
|  | Update SBDTS | 1 | 2 | 0.5 | 0 | 0.5 | ? | 2017-10-09 | 2017-10-15
Week 24 | October 16 - 22 | Module 24
|  | Continue Coding Project | 20 | 10 | 0 | 0 | 0 | ? | 2017-10-16 | 2017-10-22
|  | Project Status Update 4 | 2 | 2 | 0.5 | 0 | 0.5 | ? | 2017-10-16 | 2017-10-22
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-10-16 | 2017-10-22
Week 25 | October 23 - 29 | Module 25
|  | Continue Coding Project | 20 | 20 | 0 | 0 | 0 | ? | 2017-10-23 | 2017-10-29
|  | Project Status Update 5 | 2 | 2 | 0.5 | 0.5 | 0.5 | ? | 2017-10-23 | 2017-10-29
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-10-23 | 2017-10-29
Week 26 | October 30 - November 5 | Module 26
|  | Continue Coding Project | 10 | 25 | 0 | 0 | 0 | ? | 2017-10-30 | 2017-11-05
|  | Start Testing Project | 4 | 2 | 0 | 0 | 0 | ? | 2017-10-30 | 2017-11-05
|  | Start Software Testing Document (STD) | 2 | 2 | 0 | 0 | 0 | ? | 2017-10-30 | 2017-11-05
|  | Progress Report 2 | 3 | 2 | 0.5 | 0 | 0.5 | ? | 2017-10-30 | 2017-11-05
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-10-30 | 2017-11-05
Week 27 | November 6 - 12 | Module 27
|  | Finish Coding Project | 8 | 10 | 2 | 1 | 1 | ? | 2017-11-06 | 2017-11-12
|  | Continue Testing Project | 10 | 5 | 0 | 0 | 0 | ? | 2017-11-06 | 2017-11-12
|  | Continue Working on STD | 4 | 5 | 0 | 0 | 0 | ? | 2017-11-06 | 2017-11-12
|  | Start on User's Manual | 6 | 2 | 0 | 0 | 0 | ? | 2017-11-06 | 2017-11-12
|  | Project Status Update 6 | 2 | 1 | 0.5 | 0 | 0.5 | ? | 2017-11-06 | 2017-11-12
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-11-06 | 2017-11-12
Week 28 | November 13 - 19 | Module 28
|  | Continue Working on User's Manual | 6 | 4 | 0 | 0 | 0 | ? | 2017-11-13 | 2017-11-19
|  | Provide Project to Client for Review | 1 | 2 | 6 | 2 | 1 | ? | 2017-11-13 | 2017-11-19
|  | Finish Testing Project | 5 | 10 | 0 | 0 | 0 | ? | 2017-11-13 | 2017-11-19
|  | Continue Working on STD | 4 | 3 | 0 | 0 | 0 | ? | 2017-11-13 | 2017-11-19
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-11-13 | 2017-11-19
|  | Project Status Update 7 | 2 | 1 | 0.5 | 0.5 | 0.5 | ? | 2017-11-13 | 2017-11-19
|  | Receive Feedback from Client on Project | 1 | 1 | 6 | 2 | 1 | ? | 2017-11-13 | 2017-11-19
Week 29 | November 20 - 26 | Module 29
|  | Address Feedback from Client | 10 | 11 | 3 | 2 | 0 | ? | 2017-11-20 | 2017-11-26
|  | Finish STD | 7 | 11 | 0 | 0 | 0 | ? | 2017-11-20 | 2017-11-26
|  | Continue Working on User's Manual | 6 | 2 | 0 | 0 | 0 | ? | 2017-11-20 | 2017-11-26
|  | Revise SDD, SRS, SPMP, Risk Mitigation Plan as needed | 5 | 6 | 1 | 1 | 0.5 | ? | 2017-11-20 | 2017-11-26
|  | Update SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-11-20 | 2017-11-26
Week 30 | November 27 - December 3 | Module 30
|  | Address Feedback from Client | 5 | 5 | 0.5 | 1 | 0 | ? | 2017-11-27 | 2017-12-03
|  | Finish User's Manual | 5 | 5 | 2 | 1 | 1 | ? | 2017-11-27 | 2017-12-03
|  | Test Fixes Based on Client Feedback | 5 | 3 | 0.5 | 1 | 0 | ? | 2017-11-27 | 2017-12-03
|  | Project Status Update 8 | 2 | 1 | 0.5 | 1 | 0.5 | ? | 2017-11-27 | 2017-12-03
|  | Update SBDTS | 1 | 1 | 0.5 | 1 | 0.5 | ? | 2017-11-27 | 2017-12-03
Week 31 | December 4 - 6 | Module 31
|  | Touch Up Project and Submit | 5 | 5 | 0.5 | 0 | 5 | ? | 2017-12-04 | 2017-12-06
|  | Final Report | 5 | 2 | 1 | 1 | 2 | ? | 2017-12-04 | 2017-12-06
|  | YouTube Presentation | 3 | 5 | 1 | 1 | 2 | ? | 2017-12-04 | 2017-12-06
|  | Finish PowerPoint Presentation | 1 | 1 | 1 | 0.5 | 2 | ? | 2017-12-04 | 2017-12-06
|  | Client Acceptance Correspondence | 1 | 1 | 3 | 1 | 0.5 | ? | 2017-12-04 | 2017-12-06
|  | Finalize SBDTS | 1 | 1 | 0.5 | 0 | 0.5 | ? | 2017-12-04 | 2017-12-06

## Budget
Deliverable | Projected Hours | Actual Hours | Projected Client Hours | Actual Client Hours | Projected Mentor Hours | Actual Mentor Hours | Projected Budget | Actual Cost
SPMP | 27 | 22 | 0 | 1 | 0 | 0 | 1350 | 1150
Risk Management Plan | 13 | 10 | 0 | 0 | 1 | 0 | 725 | 500
SRS | 20 | 25 | 3 | 3 | 1 | 0 | 1225 | 1400
SDD | 20 | 15 | 4 | 2 | 2 | 0 | 1350 | 850
Presentations | 13 | 14 | 4 | 3 | 8 | 0 | 1450 | 850
User Interface Design | 24 | 12 | 6 | 1 | 0 | 0 | 1500 | 650
Project Code | 138 | 102 | 2 | 1 | 1 | 0 | 7075 | 5150
STD + Testing | 41 | 41 | 0.5 | 1 | 0 | 0 | 2075 | 2100
Client Acceptance | 18 | 20 | 15.5 | 7 | 2 | 0 | 1825 | 1350
User's Manual | 23 | 13 | 2 | 1 | 1 | 0 | 1325 | 700
Revise Deliverables | 6 | 7 | 1.5 | 1 | 1 | 0 | 450 | 400
Total | 337 | 274 | 37 | 20 | 16 | 0 | 20350 | 15100